## Protocol Completion
Somnara Protocol v1.0 — Completion Request
The hardware-to-app ACK/Error protocol is accepted as an annex. Please complete only the items below so Somnara can integrate and test the product protocol.
ID | Protocol area | Required manufacturer return | Minimum content | Status | Manufacturer response / file name
P1 | Common app → hardware frame | Final frame definition and checksum rule | Header, length meaning, sequence, opcode, payload, checksum, MTU/fragmentation rule. | AWAITING MANUFACTURER
P2 | Command payloads | One complete byte table per supported command | Set CCT, power, brightness, volume, audio, status request, RTC, alarms, sync, delete, and skip-next-alarm. | AWAITING MANUFACTURER
P3 | Device notifications | Final byte tables and timing rules | Status, alarm list, audio state, clock-valid/clock-invalid, unsolicited events, notification order. | AWAITING MANUFACTURER
P4 | Bonding and reset | Supported production bonding flow | PIN or QR method, bond storage, failed-attempt limit, re-pairing, and factory-reset behavior. | AWAITING MANUFACTURER
P5 | Sound catalog | Stable Sound ID and playback map | IDs 0–25, file name, loop/stop behavior, missing-file response, and factory-installed files. | AWAITING MANUFACTURER
P6 | Device identity | Readable identity fields and access method | Serial number, unique device ID, hardware revision, firmware revision, and factory-reset effect. | AWAITING MANUFACTURER
P7 | RCSP OTA | Tested mobile integration package | SDK version, UUIDs, transfer flow, authentication, signing, dual-bank recovery, sample UFW, and hardware compatibility check. | AWAITING MANUFACTURER
P8 | Hardware evidence | Test record for the supplied device | Firmware version, hardware revision, ACK test result, notification test result, alarm-list MTU test, and OTA recovery result. | AWAITING MANUFACTURER
Completion gate: Somnara will freeze Protocol v1.0 after the byte tables, mobile OTA material, and test evidence are supplied and checked on hardware.

## Response Instructions
How to Complete This Request
Step | Action | Return format | Reason
1 | Keep the accepted ACK/Error workbook unchanged. | No repeat response is needed. | Somnara already uses it as the hardware-to-app ACK annex.
2 | Complete the response column in Protocol Completion. | Use exact byte tables, file names, and SDK versions. | The app team must implement exact data, not assumptions.
3 | Attach SDK, UFW, and test records where requested. | ZIP or direct files with version labels. | OTA and recovery require the tested manufacturer package.
4 | Return this workbook with the hardware test-device details. | One completed Excel workbook plus files. | Somnara can then schedule the v1.0 integration test.
Please state “NOT SUPPORTED” where a requested item is not available. Do not leave a required item blank.