## Protocol Completion
Somnara Protocol v1.0 — Completion Status
The ACK/Error annex and current device-uplink definitions have been received. Supplied items are recorded below. Please complete only the remaining protocol and test items.
ID | Protocol area | Required manufacturer return | Minimum content | Status | Manufacturer response / file name
P1 | Common app → hardware frame | Final frame definition and checksum rule | Header, length meaning, sequence, opcode, payload, checksum, MTU/fragmentation rule. | AWAITING MANUFACTURER | Uplink common framing is supplied. Final APP → device frame and payload rules are still required.
P2 | Command payloads | One complete byte table per supported command | Set CCT, power, brightness, volume, audio, status request, RTC, alarms, sync, delete, and skip-next-alarm. | AWAITING MANUFACTURER | Current uplink file defines ACKs through 0x1B but does not list Skip Next 0x1C. Final command byte tables are still required.
P3 | Device notifications | Device-uplink byte tables supplied; clarification items remain | Status report 0x13 and fixed 104-byte alarm list 0x18 are supplied. Please confirm separate audio-state behavior, clock-invalid notification behavior, and whether Skip Next 0x1C is supported by current firmware. | SUPPLIED | Somnara_Device_to_APP_Protocol_Simple_EN.xlsx — current firmware protocol 0.11; firmware 0.0.2; status and all 10 alarm slots defined.
P4 | Bonding and reset | Supported production bonding flow | PIN or QR method, bond storage, failed-attempt limit, re-pairing, and factory-reset behavior. | AWAITING MANUFACTURER | NOT_BONDED exists, but status Flags is fixed at 0. Exact PIN/QR, failed-attempt, re-pairing, and reset behavior remain open.
P5 | Sound catalog | Stable Sound ID and playback map | IDs 0–25, file name, loop/stop behavior, missing-file response, and factory-installed files. | PARTIAL | Sound ID range 0–25 is confirmed in status and alarm records. File names and loop/stop behavior remain open.
P6 | Device identity | Readable identity fields and access method | Serial number, unique device ID, hardware revision, firmware revision, and factory-reset effect. | PARTIAL | Product ID, hardware revision, and firmware version are supplied in status 0x13. Serial number and unique device identity remain open.
P7 | RCSP OTA | Tested mobile integration package | SDK version, UUIDs, transfer flow, authentication, signing, dual-bank recovery, sample UFW, and hardware compatibility check. | AWAITING MANUFACTURER
P8 | Hardware evidence | Test record for the supplied device | Firmware version, hardware revision, ACK test result, notification test result, alarm-list MTU test, and OTA recovery result. | PARTIAL | Current version values are supplied. ACK, 104-byte MTU, notification, and OTA recovery test evidence remain open.
Completion gate: Somnara will freeze Protocol v1.0 after the byte tables, mobile OTA material, and test evidence are supplied and checked on hardware.

## Response Instructions
How to Complete This Request
Step | Action | Return format | Reason
1 | Keep both supplied manufacturer protocol workbooks unchanged. | No repeat response is needed for supplied byte tables. | Somnara uses them as the ACK/Error and device-uplink annexes.
2 | Complete only rows still marked AWAITING MANUFACTURER or PARTIAL. | Use exact byte tables, file names, SDK versions, and test results. | The app team must implement current firmware behavior without assumptions.
3 | Attach SDK, UFW, and test records where requested. | ZIP or direct files with version labels. | OTA and recovery require the tested manufacturer package.
4 | Return this workbook with the hardware test-device details. | One completed Excel workbook plus files. | Somnara can then schedule the v1.0 integration test.
Please state “NOT SUPPORTED” where a requested item is not available. Do not leave a required item blank.

## Audit Findings
Protocol Audit — 25 August 2026
Compared: current device-uplink workbook, accepted ACK/Error definition, Somnara v0.11 draft, completion request, and current app BLE core.
Priority | Finding | Evidence | Required action | State
BLOCKER | APP → device command bytes are not final. | The new workbook defines device → app only. | Supply the final common downlink frame and every command payload. | OPEN
CLARIFY | Skip Next 0x1C is missing from the current uplink ACK list. | ACKs are listed for 0x04–0x1B. Earlier materials allocated 0x1C. | Confirm whether firmware 0.0.2 supports 0x1C and provide its ACK behavior. | OPEN
CLARIFY | No separate Audio State frame is defined. | Status 0x13 includes Sound ID and Device State; Audio Control 0x09 receives an ACK. | Confirm whether status 0x13 is the only audio follow-up after 0x09. | OPEN
RISK | The alarm list is one 104-byte AE02 notification. | The workbook requires ATT MTU ≥107. | Provide a passing Android and iOS notification test, including negotiated MTU. | OPEN
CLARIFY | Production bonding behavior is still not defined. | NOT_BONDED exists, while status Flags is fixed at 0. | Supply PIN/QR, bond storage, failed-attempt, re-pairing, and reset behavior. | OPEN
PARTIAL | Identity is not unique yet. | Status supplies Product ID, hardware revision, and firmware 0.0.2 only. | Supply serial number and stable unique device identity reads. | OPEN
CONFIRMED | Status and complete alarm-list formats are usable. | 0x13 is 24 bytes. 0x18 is 104 bytes with ten fixed 9-byte slots and two checksums. | Implement parsers after notification dispatch is added. | SUPPLIED
APP GAP | The current app treats every AE02 packet as an ACK. | Firmware automatically sends status 0x13 with sequence 0xFF after subscription. | Add opcode dispatch before ACK parsing; then add status and alarm-list parsers. | LOCAL CHANGE NEEDED
Audit result: the new workbook is internally consistent for ACK, status, and alarm-list framing. Protocol v1.0 is not ready until the open downlink, security, identity, audio, OTA, and hardware-test items are closed.